## Phan cong
HOANTIEN - BANG PHAN CONG CONG VIEC
Tuan | Nguoi | STT | Cong viec | Trang thai | Ngay BD | Ngay HT | Ghi chu
T1 | Leader |  | Cron job tu dong sync don hang 15p | Chua lam |  |  | Vercel Cron
T1 | Leader |  | API rút tien that | Chua lam
T1 | Leader |  | API lich su giao dich | Chua lam
T1 | Leader |  | API lich su don hang tu DB | Chua lam
T1 | Dev |  | Responsive mobile toan bo trang | Chua lam
T1 | Dev |  | Animation paste link -> preview | Chua lam
T1 | Dev |  | Loading skeleton khi fetch API | Chua lam
T1 | Dev |  | Fix anh SP hien thi tren mobile | Chua lam
T2 | Leader |  | Duyet rut tien admin panel | Chua lam
T2 | Leader |  | Auto-withdraw backend logic | Chua lam
T2 | Leader |  | SEO metadata tat ca trang | Chua lam
T2 | Dev |  | Optimize anh + lazy loading | Chua lam
T2 | Dev |  | UI login/register dep hon | Chua lam
T2 | Dev |  | Toast notification login/logout | Chua lam
T2 | Dev |  | Dark mode toggle | Chua lam
T3 | Leader |  | Bot Telegram /lienket /sodu | Chua lam
T3 | Leader |  | Bot Zalo lienket sodu subid | Chua lam
T3 | Leader |  | Referral tracking that | Chua lam
T3 | Dev |  | Dashboard responsive + dep | Chua lam
T3 | Dev |  | Bieu do thu nhap ca nhan | Chua lam
T3 | Dev |  | Don hang filter sort pagination | Chua lam
T4 | Leader |  | Admin quan ly don + duyet rut | Chua lam
T4 | Leader |  | Admin quan ly nguoi dung | Chua lam
T4 | Leader |  | Deploy len VPS/Vercel | Chua lam
T4 | Leader |  | Setup domain + SSL | Chua lam
T4 | Dev |  | Test full flow dki -> mua -> rut | Chua lam
T4 | Dev |  | Viet tai lieu huong dan SD | Chua lam
T4 | Dev |  | Test cross-browser | Chua lam